## Sprint_1
|  |  |  | Week #1 (3 hrs / week) | [5 empty] | Week #2 (3 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 4 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12
|  |  |  | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11
|  |  |  | 22 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
|  |  | 24 | 24 | 23 | 22 | 21 | 19 | 17 | 15 | 11 | 7 | 5 | 3 | 0
Research and decide on the UI, UX designs, technologies to be leveraged for the development | Decide the tech stack to be used for the frontend. | Sai Krishna | 6 | 6 | 6 | 6 | 5 | 5 | 4 | 4 | 2 | 2 | 1 | 0 | 0
| Draw up Wireframes for a few pages | Pavan | 6 | 6 | 6 | 6 | 6 | 5 | 4 | 4 | 4 | 2 | 1 | 1 | 0
Research and decide on the holistic architecture and database schema, designs to be implemented. | Decide on DB schema, different technologies to achieve them. | Teja | 6 | 6 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 1 | 1 | 0
| Decide on architecture and design the architecture diagram | Lahari | 6 | 6 | 6 | 5 | 5 | 4 | 5 | 4 | 3 | 2 | 2 | 1 | 0
Team:
Sai Krishna | 3 hours / Week
Teja | 3 hours / Week
Lahari | 3 hours / Week
Pavan K | 3 hours / Week
Total Available Hours During Sprint: | 24

## Sprint_2
|  |  |  | Week #1 (3 hrs / week) | [5 empty] | Week #2 (3 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 4 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12
|  |  |  | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24
|  |  |  | 22 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
|  |  | 24 | 23 | 22 | 20 | 19 | 16 | 13 | 9 | 7 | 6 | 3 | 2 | 0
Setting up local systems with the requried environments. | Set up AWS RDS, Java, MySQL workbench, Postman | Pavan | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 2 | 1 | 1 | 1 | 0
| POC setup, setting up AWS RDS, Java, MySQL workbench, Postman environments | Sai Krishna | 5 | 5 | 5 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 0 | 0 | 0
| Set up AWS RDS, Java, MySQL workbench, Postman | Lahari | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 0
| Set up AWS RDS, Java, MySQL workbench, Postman | Teja | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 0 | 0
Create more wireframes. | Create the wireframe for Login page. | Pavan | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Research on UI templates | Peruse multiple templates and decide one. | Sai Krishna | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decide on the documentation | Finalize the tool for project tracking | Lahari | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Setup the backend. | Create Spring boot project using Spring initalizer. | Teja | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team:
Sai Krishna | 3 hours / Week
Teja | 3 hours / Week
Lahari | 3 hours / Week
Pavan K | 3 hours / Week
Total Available Hours During Sprint: | 24

## Sprint_3
|  |  |  | Week #1 (6 hrs / week) | [5 empty] | Week #2 (6 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 4 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12
|  |  |  | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07
|  |  |  | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
|  |  | 48 | 48 | 47 | 43 | 41 | 38 | 34 | 31 | 26 | 20 | 18 | 9 | 0
Work on the UI of multiple pages | Create the UI of homepage. | Sai Krishna | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 2 | 0
| Create the wireframe for home page. | Pavan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 3 | 3 | 1 | 0
| Create the User profile page. | Pavan | 6 | 6 | 6 | 6 | 6 | 5 | 4 | 4 | 3 | 3 | 3 | 2 | 0
| Create the UI of booking history page. | Sai Krishna | 6 | 6 | 5 | 5 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 0 | 0
Create the APIs and respective validations | API validations for hotel search | Lahari | 6 | 6 | 6 | 5 | 5 | 5 | 4 | 4 | 3 | 1 | 1 | 1 | 0
| Booking API | Teja | 6 | 6 | 6 | 5 | 5 | 4 | 4 | 4 | 4 | 2 | 2 | 1 | 0
| API validations for hotel search | Teja | 6 | 6 | 6 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 1 | 0
| Functionality of Login | Lahari | 6 | 6 | 6 | 5 | 5 | 4 | 3 | 3 | 3 | 2 | 2 | 1 | 0
Team:
Sai Krishna | 6 hours / Week
Teja | 6 hours / Week
Lahari | 6 hours / Week
Pavan K | 6 hours / Week
Total Available Hours During Sprint: | 48

## Sprint_4
|  |  |  | Week #1 (6 hrs / week) | [5 empty] | Week #2 (6 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 4 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12
|  |  |  | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21
|  |  |  | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
|  |  | 48 | 48 | 46 | 41 | 38 | 37 | 36 | 32 | 26 | 23 | 19 | 10 | 0
Implement the modify payment & Admin APIs | Create the Modify, delete booking API | Lahari | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 2 | 0
| Create the Admin API. | Teja | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 1 | 0
| Make necessary modifications and test the Admin API | Lahari | 6 | 6 | 6 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 2 | 0
| Make necessary modifications and test the delete/modify API | Teja | 6 | 6 | 5 | 5 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 0 | 0
Build the remaining page's UI | Create the Login popup page and functionaltiy. | Sai Krishna | 6 | 6 | 5 | 5 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 0
| Create the booking page and relevant wireframe. | Pavan K | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 1 | 0
Touch ups to the UI | First round of UI touchups. | Sai Krishna | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 3 | 2 | 1 | 0 | 0
| Second round of UI touchups. | Pavan K | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 4 | 3 | 3 | 2 | 0
Team:
Sai Krishna | 6 hours / Week
Teja | 6 hours / Week
Lahari | 6 hours / Week
Pavan K | 6 hours / Week
Total Available Hours During Sprint: | 48

## Sprint_5
|  |  |  | Week #1 (6 hrs / week) | [5 empty] | Week #2 (6 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 4 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12
|  |  |  | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04
|  |  |  | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
|  |  | 48 | 45 | 42 | 35 | 34 | 28 | 24 | 24 | 19 | 14 | 12 | 6 | 0
Integrate the backend and frontend and resolve the issues followed. | Resolves the issues of frontend and backend. | Pavan | 12 | 12 | 11 | 10 | 10 | 8 | 8 | 8 | 7 | 5 | 3 | 2 | 0
| Integration of frontend and backend. | Sai Krishna | 12 | 11 | 10 | 8 | 7 | 7 | 4 | 4 | 4 | 3 | 3 | 1 | 0
Deploy the porject onto AWS and resolve issues if any. | Deploying the application onto AWS. | Lahari | 12 | 11 | 10 | 8 | 8 | 5 | 5 | 5 | 3 | 3 | 3 | 2 | 0
| Setup the deployment environment (EC2, Load Balancers) | Teja | 12 | 11 | 11 | 9 | 9 | 8 | 7 | 7 | 5 | 3 | 3 | 1 | 0
Team:
Sai Krishna | 6 hours / Week
Teja | 6 hours / Week
Lahari | 6 hours / Week
Pavan K | 6 hours / Week
Total Available Hours During Sprint: | 48

## Sprint_6
Week #1 (6 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 4 x 6) | D1 | D2 | D3 | D4 | D5 | D6
|  |  |  | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11
|  |  |  | 24 | 20 | 16 | 12 | 8 | 4
|  |  | 24 | 24 | 24 | 18 | 14 | 11 | 0
Deploy the porject onto AWS and resolve issues if any. | Deploying the application onto AWS. | Lahari | 6 | 6 | 6 | 4 | 3 | 2 | 0
| Setup the deployment environment (EC2, Load Balancers) | Teja | 6 | 6 | 6 | 4 | 3 | 3 | 0
Integrate the backend and frontend and resolve the issues followed. | Resolves the issues of frontend and backend. | Pavan | 6 | 6 | 6 | 5 | 4 | 3 | 0
| Integration of frontend and backend. | Sai Krishna | 6 | 6 | 6 | 5 | 4 | 3 | 0
Team:
Sai Krishna | 6 hours / Week
Teja | 6 hours / Week
Lahari | 6 hours / Week
Pavan K | 6 hours / Week
Total Available Hours During Sprint: | 24